## Slide 1: KZN ECD RELIEF PROJECT
UPDATE

## Slide 2: Activities
TREE translated the Play at home with your children booklet from English into IsiZulu and the Signs of distress document, this was to assist ITEC.
TOT was on the 25th and 26th of May 2022 at TREE offices.
In preparation for the TOT, TREE designed;
Attendance registers for parents and practitioners (and printed for all RTO’s)
Travel log sheets for trainers (and printed for all RTO’s)
Pre and post tests (and printed for all RTO’s)
Certificates for the practitioners and parents

## Slide 3: Activities
On a weekly basis TREE receives the following from RTO’s
Attendance registers
Pre and post tests
Report
A spreadsheet of the weekly reach is updated and sent to partners.
Support is provided to RTO’s telephonically and via email as and when RTO’s need it.
Assist NECT with information when they request it.
Assist UNICEF with information when they request it.

## Slide 4: Challenges
There was a shortage of Repurpose for Purpose materials, 30 activity cards and 95 playbooks. DMF will send through the activity cards and NECDA will be paying for the printing of the 95 playbooks.
Reporting lines have blurred as TREE is no longer solely reporting to NECDA but is also receiving direct communication/requests from the funders.
RTO’s are reporting that 1 day is a tight squeeze to complete 2 topics for practitioners i.e. Repurpose for purpose and Self Care.

## Slide 5: REACH
 | Target | Reach as of week 2
Practitioners | 1000 | 331
Parents | 2000 | 446
ECD Centres | 55 | 289
Children | - | 13597
All RTO’s are on track accordingly with their implementation plans.
4 weeks of training remaining.

## Slide 6: THANK YOU!!!